## Revision History
Version | Description of Change | Updated By | Date
1 | Initial Assessment for documentation deliverables | Thomas Renneberg | December 2025
Purpose | This record tracks the documentation deliverables for HAI-RadX Suite. Prior to commencing development, as part of the release planning all documents requiring update have been identified. This record is then tracked the updates, reviews and approvals of these document to ensure all activities have been completed prior to release.
Abbreviation | Document Category
HAI | Harrison
PRJ | Project Management
PRM | Product Management
SYS | System
SW | Software
DPL | Deployment
CLI | Clinical
RA | Regulatory Affairs
QA | Quality Assurance
VNV | Verification & Validation
AU | Australia
NZ | New Zealand
EU | European Union
UK | United Kingdom
MY | Malaysia
TH | Thailand
NA | Not Applicable

## OLD - Run Sheet - 3.6 - OLD (hidden)
Deliverable | Area | Document ID - Title | Version | SC CTB | Data Purge | Model 3.1 | Harness | TB | Reporting | Owner | Notes
Planning | Development Plan | OPT-PRJ-001 - Design & Development Plan | 12 | To Do | To Do | To Do | No Change | To Do | To Do | Thomas
| XFT Definition | OPT-PRJ-002 - XFT Definition | 18 | No Change | To Do | To Do | To Do | To Do | To Do | Thomas
Design Inputs | Intended Purpose | OPT-PRM-002 - Use Specification | 13 | To Do | To Do | No Change | No Change | To Do | No Change | Kieran | INvestigate TB use spec
| Regulatory Strategy | OPT-RA-007 Applicable Standards and Guidance Documents | 6 | To Do | To Do | To Do | No Change | To Do | No Change | Kingston | WIll need to review (both ROW and US space) Nothing yet found
|  | OPT-RA-017 Regulatory Strategy Plan for Annalise Enterprise -CXR and CTB | 9 | To Do | To Do | To Do | No Change | To Do | No Change | Kingston | No for US, Review for ROW
| Product Inputs | OPT-CLI-002 Ontology Tree Specification | 9 | No Change | No Change | To Do | No Change | To Do | No Change | Rejo | Dolthub
|  | OPT-CLI-047 CTB Annalise Enterprise CTB Findings Specification | 12 | No Change | No Change | No Change | No Change | No Change | No Change | Rejo
|  | OPT-PRM-001 - Input Requirements | 16 | To Do | To Do | To Do | No Change | To Do | To Do | PO | Responsibility to be discussed
Risk Management | Risk Management Plan | OPT-SYS-001 - Risk Management Plan | 6 | To Do | To Do | To Do | No Change | To Do | To Do | Chrishan | Harness Installation FMEA
| Preliminary Risk Analysis | OPT-SYS-002 - Risk Analysis Report | 14 | To Do | To Do | To Do | To Do | To Do | To Do | Sean
| Cybersecurity Assessment | OPT-SYS-006 - Cybersecurity Risk Analysis | 15 | No Change | To Do | To Do | To Do | No Change | To Do | Chrishan | Hard to say for reporting
| Final Risk Analysis | OPT-SYS-002 - Risk Analysis Report | 14 | To Do | To Do | To Do | To Do | To Do | To Do | Sean
| Risk Management Report | OPT-SYS-002 - Risk Analysis Report | 14 | To Do | To Do | To Do | To Do | To Do | To Do | Sean
Usability / Human Factors | Use Specification | OPT-PRM-002 - Use Specification | 13 | To Do | To Do | No Change | No Change | To Do | No Change | Kieran
| Hazard Related Use Scenarios / Critical Tasks | OPT-SYS-002 - Risk Analysis Report | 14 | To Do | To Do | To Do | To Do | To Do | To Do | Sean
| Human Factors | OPT-SYS-031 Annalise Enterprise Triage Human Factors Engineering Evaluation | 1 | No Change | No Change | No Change | No Change | No Change | No Change | Kiet | Kiet to review for update
| User Interface Evaluation Plan | OPT-SYS-007 - Usability Engineering Summary | 5 | To Do | To Do | No Change | No Change | No Change | To Do | Kiet | Likely for reporting, assess for other areas
| Formative Evaluation | OPT-CLI-010 - Formative Evaluation | 0 | No Change | To Do | No Change | No Change | No Change | To Do | Kiet | Need for reporting
|  | OPT-CLI-012 Release 1.1 Formative Evaluation | 0 | No Change | No Change | No Change | No Change | No Change | No Change
|  | OPT-CLI-059 Release 3.0 Formative Evaluation | 0 | No Change | No Change | No Change | No Change | No Change | No Change
|  | OPT-CLI-118 Release 3.4 Formative Evaluation | 0 | No Change | No Change | No Change | No Change | No Change | No Change
| Summative Evaluation Protocol | OPT-CLI-011 - Summative Evaluation | 4 | No Change | No Change | No Change | No Change | No Change | No Change
| Summative Evaluation Report | OPT-CLI-011 - Summative Evaluation | 4 | No Change | No Change | No Change | No Change | No Change | No Change
Requirements and Specifications | Software Requirements | OPT-SYS-038 Annalise Enterprise Integration Adapter Software Requirements Specification | 11 | To Do | To Do | To Do | No Change | To Do | To Do |  | PO's to advise on what requirements fall where for updates
|  | OPT-SYS-040 Annalise Enterprise Backend Software Requirements Specification | 10 | To Do | To Do | To Do | No Change | To Do | To Do |  | PO's to advise on what requirements fall where for updates
|  | OPT-SYS-032 Annalise Viewer Software Requirements Specification | 6 | To Do | To Do | To Do | No Change | To Do | No Change |  | PO's to advise on what requirements fall where for updates
|  | OPT-SYS-025 Annalise Viewer Adapter for Sectra IDS7 | 2 | No Change | No Change | No Change | No Change | No Change | No Change
| Interface Specifications | OPT-SW-024 Annalise Integration Adapter API Specification | 2 | No Change | No Change | No Change | No Change | No Change | To Do |  | Need TL advice
|  | OPT-SW-018 - PACS Viewer API specifications | 0 | No Change | No Change | No Change | No Change | No Change | No Change
|  | OPT-SW-021 - Annalise Viewer Open API Specification | 5 | No Change | No Change | No Change | No Change | No Change | No Change
|  | OPT-SW-007 DICOM and HL7 Specification | 10 | To Do | To Do | To Do | No Change | To Do | To Do |  | Need TL advice
| Accompanying Documentation Specifications | OPT-VNV-020 - Accompanying Documentation Specification and Verification Protocol | 11 | To Do | To Do | To Do | No Change | To Do | To Do | Rejo
Design Outputs | Software Architecture and Design Description | OPT-SW-001 - Software Architecture and Design Description | 10 | To Do | To Do | To Do | No Change | No Change | No Change | Varun
|  | OPT-SW-025 - Backend Services Architecture and Design Description | 6 | To Do | To Do | To Do | No Change | No Change | No Change | Varun
|  | OPT-SW-026 - Annalise Viewer Architecture Design Description | 6 | To Do | To Do | To Do | No Change | No Change | No Change | Max
|  | OPT-SW-027 - Integration Adapter Architecture and Design Description | 6 | To Do | To Do | To Do | No Change | No Change | No Change | Varun
|  | OPT-SW-029 - Annalise Viewer Adapter for Sectra IDS7 Architecture and Design Description | 1 | No Change | No Change | No Change | No Change | No Change | No Change
|  | OPT-SW-002 - Architecture and Detailed Design Description for CXR AI Services | 6 | No Change | No Change | To Do | No Change | To Do | No Change | Rejo
|  | OPT-SW-053 - Architecture and Detailed Design Descriptionfor CTB AI Services | 2 | No Change | No Change | No Change | No Change | No Change | No Change
| SOUP / OTS Acceptance Record | OPT-SW-043 - Annalise Backend Services OTS Software Acceptance Report | 9 | To Do | To Do | To Do | No Change | No Change | To Do | Jen
|  | OPT-SW-039 - Annalise Integration Adapter OTS Software Acceptance Report | 6 | To Do | To Do | To Do | No Change | No Change | To Do | Jen
|  | OPT-SW-003 - Annalise Viewer OTS Software Acceptance Report | 16 | To Do | To Do | To Do | No Change | No Change | No Change | Max
|  | OPT-SW-038 - Annalise Viewer Adapter for Sectra IDS7 OTS Software Acceptance Report | 0 | No Change | No Change | No Change | No Change | No Change | No Change
| Design Reviews | OPT-SYS-068 Design Review Minutes for Adding Support for Thick Slices for US | 1 | No Change | No Change | No Change | No Change | No Change | No Change
|  | OPT-SYS-028 - Design review for Data Purge | 0 |  | To Do | No Change | No Change | No Change
|  | OPT-SYS-043 - Design review for CXR Connector | 0 |  | No Change | To Do | No Change | No Change
|  | OPT-SYS-045 - Design review for Viewer 3.5 | 0 | To Do | To Do | No Change | No Change | No Change | To Do
| Model Development Plan | OPT-SW-054 - Model Development Plan: CTB Attributes Model | 1 | No Change | No Change | No Change | No Change | No Change | No Change
|  | OPT-SW-055 - Model Development Plan: CTB Registration Model | 2 | No Change | No Change | No Change | No Change | No Change | No Change
|  | OPT-SW-056 - Model Development Plan: CT Brain Model | 1 | No Change | No Change | No Change | No Change | No Change | No Change
|  | OPT-SW-070 - AI Model Development Plan: CXR Model | 0 | No Change | No Change | No Change | No Change | No Change | No Change
|  | OPT-SW-071 - AI Model Development Plan: CXR Attributes Model | 0 | No Change | No Change | To Do | No Change | To Do | No Change | AI Dev | Will be fully new plan for CXR
| Model Development Record | OPT-SW-057 - Model Development Record: CTB Attributes Model | 2 | No Change | No Change | To Do | No Change | To Do | No Change | AI Dev
|  | OPT-SW-058 - Model Development Record: Registration Model | 1 | No Change | No Change | To Do | No Change | To Do | No Change | AI Dev
|  | OPT-SW-059 - Model Development Record: CT Brain Model | 3 | No Change | No Change | To Do | No Change | To Do | No Change | AI Dev
|  | OPT-SW-072 - Model Development Record: CXR Model | 0 | No Change | No Change | To Do | No Change | To Do | No Change | AI Dev | Pending AI dev
| Software Build Records | OPT-SW-028 - Annalise Viewer Release Candidates | 22 | To Do | To Do | To Do | No Change | To Do | No Change | Max
|  | OPT-SW-030 - Annalise Backend Release Candidates | 31 | To Do | To Do | To Do | No Change | To Do | To Do | Jen
|  | OPT-SW-090 Annalise Backend Infrastructure Release Candidates | 2 |  | To Do | To Do | No Change | To Do
|  | OPT-SW-031 - Annalise Integration Adapter Release Candidates | 19 | To Do | To Do | To Do | No Change | To Do | To Do | Jen
|  | OPT-SW-041 Annalise Integration Adapter Infrastructure Release Candidates | 2 |  | To Do | To Do | No Change | To Do
|  | OPT-SW-037 Annalise Viewer Adapter for Sectra IDS7 Release Candidates | 2 | No Change | No Change | No Change | No Change | No Change | No Change
| Transfer Plan | OPT-PRJ-007 - Design Transfer Plan | 5 | No Change | No Change | No Change | No Change | No Change | No Change
| Deployment, Installation, Configuration Processes | OPT-SW-060 - Software Configuration Management Plan | 0 | No Change | No Change | No Change | No Change | No Change | No Change
|  | OPT-SYS-010 - Installation Requirements | 8 | To Do | To Do | To Do | To Do | No Change | No Change | Chrishan
|  | OPT-DPL-228 - Annalise Backend 3.6.0 On-Prem Deployment Run Sheet | 0 | To Do | To Do | To Do | No Change | No Change | No Change | TL
|  | OPT-DPL-011 - On-prem Annalise Backend Configuration Run Sheet | 11 | To Do | To Do | To Do | No Change | No Change | No Change | TL
|  | OPT-DPL-012 - Cloud Configuration Run Sheet | 11 | To Do | To Do | To Do | No Change | No Change | No Change | TL
|  | OPT-DPL-227 - Annalise Integration Adapter 3.6.0 Deployment Run Sheet | 0 | To Do | To Do | To Do | No Change | No Change | No Change | TL
|  | OPT-DPL-229 - Annalise Backend 3.6.0 Cloud Deployment Run Sheet | 0 | To Do | To Do | To Do | To Do | No Change | No Change | TL
Verification and Validation | Regression Analysis | OPT-SYS-012 Regression Analysis | 35 | To Do | To Do | To Do | No Change | No Change | To Do | Rejo | Rejo to commence work towards regression
| Verification Plan and Protocol | OPT-VNV-001 Annalise Enterprise Verification Plan | 10 | To Do | To Do | To Do | No Change | No Change | To Do | Test
|  | OPT-VNV-030 - Annalise Viewer Verification Protocol | 6 | No Change | No Change | No Change | No Change | No Change | No Change | Test
|  | OPT-VNV-031 - Backend and Viewer Compatibility Protocol | 5 | To Do | To Do | No Change | No Change | No Change | No Change | Test
|  | OPT-VNV-032 - Backend Services Verification Protocol | 7 | To Do | To Do | To Do | No Change | No Change | To Do | Test
|  | OPT-VNV-033 - Annalise Enterprise Integration Adapter Verification Protocol | 10 | To Do | To Do | No Change | No Change | No Change | To Do | Test
|  | OPT-VNV-043 - Compatibility of Backend and Integration Adapter Verification Protocol | 5 | To Do | To Do | No Change | No Change | No Change | To Do | Test
|  | OPT-VNV-035 Annalise Viewer Adapter for Sectra IDS7 Verification Protocol | 1 | To Do | To Do | No Change | No Change | No Change | No Change | Test
|  | OPT-VNV-010 - Security Testing Protocol | 5 | To Do | To Do | No Change | No Change | No Change | To Do | Test
|  | OPT-VNV-013 - Integration Adapter Performance Verification Protocol | 7 | To Do | To Do | No Change | No Change | No Change | No Change | Test
|  | OPT-VNV-080 Integration Verification Protocol | 0 | To Do | To Do | No Change | No Change | No Change | No Change | Test
|  | OPT-VNV-068 - Backend Performance Verification Protocol | 4 | To Do | To Do | No Change | No Change | No Change | No Change | Test
|  | OPT-VNV-007 - CXR Attributes Model Performance | 1 | To Do | To Do | To Do | No Change | No Change | No Change
|  | OPT-VNV-059 - CTB Attributes Evaluation Protocol | 2 | To Do | To Do | No Change | No Change | No Change | No Change
|  | OPT-VNV-063 - Installation and Upgrade Verification Protocol | 5 | To Do | To Do | No Change | No Change | No Change | To Do
|  | OPT-VNV-020 - Accompanying Documentation Specification and Verification Protocol | 11 | To Do | To Do | To Do | No Change | To Do | To Do
| Verification Results | OPT-VNV-003 AWS Cloud Security | 4 | To Do | To Do | To Do | No Change | To Do | To Do
|  | OPT-VNV-007 - Attributes Model Performance | 1 | To Do | To Do | To Do | No Change | To Do | To Do
|  | OPT-VNV-056 - CTB Attributes Model Evaluation Report | 2 | To Do | To Do | To Do | No Change | To Do | To Do
|  | OPT-VNV-011 - Installation and Upgrade Verification Results | 11 | To Do | To Do | To Do | No Change | To Do | To Do
|  | OPT-VNV-015 - Integration Adapter Performance Verification Report | 10 | To Do | To Do | To Do | No Change | To Do | To Do
|  | OPT-VNV-069 - Backend Performance Verification Report | 6 | To Do | To Do | To Do | No Change | To Do | To Do
|  | OPT-VNV-014 - Security Pentesting Report | 7 | To Do | To Do | To Do | No Change | To Do | To Do
|  | OPT-VNV-070 - Annalise Viewer Verification Report | 8 | To Do | To Do | To Do | No Change | To Do | To Do
|  | OPT-VNV-034 - Backend and Viewer Compatibility Verification Results | 6 | To Do | To Do | To Do | No Change | To Do | To Do
|  | OPT-VNV-023 - Integration Adapter Verification Results | 11 | To Do | To Do | To Do | No Change | To Do | To Do
|  | OPT-VNV-044 - Compatibility of Backend and Integration Adapter Verification Results | 5 | To Do | To Do | To Do | No Change | To Do | To Do
|  | OPT-VNV-024 - Annalise Backend Cloud Verification Results - Test results for BE 3.4.0-0003 | 12 | To Do | To Do | To Do | No Change | To Do | To Do
|  | OPT-VNV-025 - Annalise Backend On-Prem Verification Results | 12 | To Do | To Do | To Do | No Change | To Do | To Do
|  | OPT-VNV-045 - Annalise Viewer Adapter for Sectra Workstation IDS7 Verification Report | 1 | To Do | To Do | To Do | No Change | To Do | To Do
|  | OPT-VNV-076 - Model Integration Regression Report | 2 | To Do | To Do | To Do | No Change | To Do | To Do
|  | OPT-VNV-081 Integration Verification Report | 0 | To Do | To Do | To Do | No Change | To Do | To Do
|  | OPT-VNV-073 CTB Triage Effectiveness Evaluation Report | 0 | To Do | To Do | To Do | No Change | To Do | To Do
|  | OPT-VNV-026 - Accompanying Documentation Verification Results | 10 | To Do | To Do | To Do | No Change | To Do | To Do
| CSV | ANN-SW-016 Annalise Viewer Test Automation Framework Validation Protocol | 1 | To Do | To Do | To Do | No Change | To Do | To Do
|  | ANN-SW-005 Thanos Test System Validation Protocol | 9 | To Do | To Do | To Do | No Change | To Do | To Do
|  | ANN-SW-024 Integration Adapter Test Tools Validation Protocol | 2 | To Do | To Do | To Do | No Change | To Do | To Do
|  | ANN-SW-007 - Deployment Smoke Test Validation Protocol | 4 | To Do | To Do | To Do | No Change | To Do | To Do
|  | ANN-SW-006 - Enterprise K6 Tests Computer System Validation Protocol | 6 | To Do | To Do | To Do | No Change | To Do | To Do
|  | ANN-SW-017 Viewer Test Automation Framework Validation Report | 5 | To Do | To Do | To Do | No Change | To Do | To Do
|  | ANN-SW-023 - Thanos Test System Validation Results | 4 | To Do | To Do | To Do | No Change | To Do | To Do
|  | ANN-SW-025 Integration Adapter Test Tools Validation Results | 3 | To Do | To Do | To Do | No Change | To Do | To Do
|  | ANN-SW-041 - Deployment Smoke Test Validation Report | 2 | To Do | To Do | To Do | No Change | To Do | To Do
|  | ANN-SW-020 Enterprise K6 Tests Computer System Validation Report | 1 | To Do | To Do | To Do | No Change | To Do | To Do
|  | Thanos CSV Impact Assessment (DOC-2600) | 2 | To Do | To Do | To Do | No Change | To Do | To Do
|  | Integration Adapter Test Tools Impact Assessment (DOC-2812) | 0 | To Do | To Do | To Do | No Change | To Do | To Do
|  | K6 CSV Impact Assessment (DOC-2340) | 3 | To Do | To Do | To Do | No Change | To Do | To Do
| Validation Plan and Protocols | OPT-VNV-002 - Validation Plan & Protocol | 12 | To Do | To Do | To Do | No Change | To Do | To Do | Sean L
| Validation Results & Records | OPT-VNV-006 - Annalise Enterprise Validation Report | 12 | To Do | To Do | To Do | No Change | To Do | To Do | Sean L
| Trace Matrix | OPT-SYS-009 Verification & Validation Summary (Traceability Matrix) | 21 | To Do | To Do | To Do | No Change | To Do | To Do | Sean L
| Residual Anomalies | OPT-PRJ-004 - Deferred Issues | 14 | To Do | To Do | To Do | No Change | To Do | To Do | Rejo
|  | OPT-CLI-042 Clinical Evaluation Plan (CEP) for Annalise Enterprise | 2 | No Change | No Change | To Do | No Change | No Change | No Change | Nalan
|  | OPT-CLI-027 AI Model Comparison Protocol | 1 | No Change | No Change | To Do | No Change | No Change | No Change | Megan
|  | OPT-CLI-007 - Non-inferiority Evaluation Protocol | 7 | No Change | No Change | No Change | No Change | No Change | No Change
|  | OPT-CLI-038 - Literature Review Protocol Annalise Enterprise (CXR Model) | 2 | No Change | No Change | No Change | No Change | No Change | No Change
|  | OPT-CLI-121 - Standalone Performance Evaluation Protocol – CXR Tuberculosis AI Model | 0 |  | No Change | No Change | No Change | To Do | No Change
|  | OPT-VNV-082 CXR View Position Evaluation Protocol | 0 |  | No Change | To Do | No Change | To Do |  | Slany
|  | OPT-CLI-003 - Multi-Reader Multi-Case Study | 3 | No Change | No Change | No Change | No Change | No Change | No Change
|  | OPT-CLI-031 - Clinical Justification for Time-Sensitive Findings | 1 | No Change | No Change | No Change | No Change | No Change | No Change
| Supporting Docs - CXR | OPT-CLI-077 - Annalise Enterprise CXR Triage Trauma Performance Evaluation Summary | 3 | No Change | No Change | No Change | No Change | No Change | No Change
| Study Reports - CXR | OPT-CLI-122 - Standalone Performance Evaluation Report - CXR AI Module - Suspected TB | 0 | No Change | No Change | No CHange | No Change | To Do | No Change |  | This will be obsoleted shortly
|  | OPT-CLI-008 - CXR Non-inferiority Evaluation Report | 9 | No Change | No Change | To Do | No Change | No Change | No Change | Megan | Should we also add the Annexes which include the output of the model eval scripts?
|  | OPT-CLI-037 - CXR Radiologist Augmentation Study Report | 1 | No Change | No Change | No Change | No Change | No Change | No Change
|  | OPT-CLI-040 - Annalise Enterprise CXR Model Literature Evaluation Matrix | 2 | No Change | No Change | To Do | No Change | No Change | No Change | Nalan
|  | OPT-CLI-098 - CXR Model Comparison Report | 0 | No Change | No Change | To Do | No Change | No Change | No Change | Megan | Should we also add the Annexes which include the output of the model comparison scripts?
|  | OPT-CLI-041 - Literature Review Report for Annalise Enterprise CXR Model | 2 | No Change | No Change | To Do | No Change | No Change | No Change | Nalan
|  | OPT-VNV-083 CXR View Position Evaluation Report | 0 |  | No Change | To Do | No Change | To Do |  | Slany
|  | OPT-CLI-043 - Standalone Performance Evaluation Report | 3 | No Change | No Change | No Change | No Change | No Change | No Change
| Protocols - CTB | OPT-CLI-016 - CTB Radiologist Performance Assessment Protocol | 4 | No Change | No Change | No Change | No Change | No Change | No Change
|  | OPT-CLI-021 - CTB Radiologist Augmentation study protocol | 3 | No Change | No Change | No Change | No Change | No Change | No Change
|  | OPT-CLI-023 - CTB Non-inferiority Analysis Protocol | 6 | No Change | No Change | No Change | No Change | No Change | No Change
|  | OPT-CLI-048 - Statistical Analysis Plan for OPT-CLI-021 CTB Radiologist Augmentation Study | 1 | No Change | No Change | No Change | No Change | No Change | No Change
|  | OPT-CLI-030 - Statistical Analysis Plan for OPT-CLI-023 CTB Non-inferiority Analysis Protocol | 2 | No Change | No Change | No Change | No Change | No Change | No Change
|  | OPT-CLI-039 - Literature Review Protocol - Annalise Enterprise CTB | 2 | No Change | No Change | No Change | No Change | No Change | No Change
| Supporting Docs - CTB | OPT-CLI-014 - CTB Training Doumentation for Radiologist Readers in Protocols OPT-CLI-016 and OPT-CLI-021 | 3 | No Change | No Change | No Change | No Change | No Change | No Change
|  | OPT-CLI-025 - Optimus CTB Reader Ontology Tree | 3 | No Change | No Change | No Change | No Change | No Change | No Change
|  | OPT-CLI-092 - Annalise Enterprise CTB Performance Evaluation Summary | 2 | No Change | No Change | No Change | No Change | No Change | No Change
|  | OPT-CLI-093 - CTB Clinical Justification for Time Sensitive Findings | 5 | No Change | No Change | No Change | No Change | No Change | No Change
|  | OPT-CLI-094 - Annalise Enterprise CTB Triage Trauma Performance Evaluation Summary Part 1 | 1 | No Change | No Change | No Change | No Change | No Change | No Change
| Study Reports - CTB | OPT-CLI-095 - Annalise Enterprise CTB Triage Trauma Standalone Performance Study Report | 4 | No Change | No Change | To Do | No Change | No Change | No Change |  | Rejo - can you see if we do need these
|  | OPT-CLI-050 - Clinical Study Report for CTB Protocols OPT-CLI-021 and OPT-CLI-016 | 2 | No Change | No Change | No Change | No Change | No Change | No Change
|  | OPT-CLI-051 - Clinical Study Report for OPT-CLI-023 CTB Non-Inferiority Analysis | 6 | No Change | No Change | No Change | No Change | No Change | No Change | Georgie | Should we also add the Annexes which include the output of the model eval scripts?
|  | OPT-CLI-052 - Annalise Enterprise CTB Model Literature Review Report | 2 | No Change | No Change | To Do | No Change | No Change | No Change | Nalan
|  | OPT-CLI-053 - Annalise Enterprise CTB Literature Review Matrix | 2 | No Change | No Change | To Do | No Change | No Change | No Change | Nalan
|  | OPT-CLI-060 - Annalise Enterprise CTB Model Comparison Report | 4 | No Change | No Change | To Do | No Change | No Change | No Change | Georgie | Should we also add the Annexes which include the output of the model comparison scripts?
|  | OPT-CLI-049 - Data Monitoring Report for OPT-CLI-021 Radiologist Augmentation Study | 0 | No Change | No Change | No Change | No Change | No Change | No Change
| Summary Docs | OPT-CLI-107 US Product Performance Summary | 1 |  | To Do | No Change | No Change | No Change
| Clinical Evaluation Docs | OPT-CLI-120 - Benefit-Risk Analysis for Annalise Triage | 0 |  | To Do | No Change | No Change | No Change |  | Nalan
|  | OPT-CLI-119 Benefit-Risk Analysis for Annalise Enterprise | 0 | To Do | No Change | To Do | No Change | To Do | No Change | Nalan | Reporting?
|  | Note to File | 0 |  | No Change | To Do | No Change | To Do |  | Nalan
|  | OPT-CLI-044 Clinical Evaluation Report (CER) for Annalise Enterprise | 5 | To Do | No Change | No Change | No Change | No Change | No Change
| NHS Safety Reort | OPT-CLI-117 Clinical Safety Case Report | 3 |  | No Change | No Change | No Change | No Change |  | Minta/Nalan | Update for NHS requirements
Design Transfer and Release | Transfer Plan | OPT-PRJ-007 - Design Transfer Plan | 5 | No Change | To Do | To Do | No Change | No Change | No Change | THomas | To confirm no update
| Software Release Record | OPT-SW-100 - Annalise Viewer v3.6 Release Report | 0 | To Do | To Do | To Do | No Change | To Do | No Change
|  | OPT-SW-101 - Annalise Backend Services v3.6 Release Report | 0 | To Do | To Do | To Do | No Change | To Do | To Do
|  | OPT-SW-102 - Annalise Integration Adapter v3.6 Release Report | 0 | To Do | To Do | To Do | No Change | To Do | To Do
|  | OPT-SW-040 - Annalise Viewer Adapter for Sectra IDS7 v1.0 Release Report | 0 | No Change | No Change | No Change | No Change | No Change | No Change
| Software Bill of Materials | OPT-SW-103 - Annalise Backend Software 3.6 BOM | 0 | To Do | To Do | To Do | No Change | To Do | To Do
|  | OPT-SW-104 - Annalise Integration Adapter Software 3.6 BOM | 0 | To Do | To Do | To Do | No Change | To Do | To Do
|  | OPT-SW-105 - Annalise Viewer Software 3.6 BOM | 0 | To Do | To Do | To Do | No Change | To Do | No Change
| Guides | OPT-PRM-027 - Annalise Enterprise User Guide | 3 | To Do | To Do | To Do | No Change | To Do | To Do
|  | OPT-PRM-028 - Annalise Enterprise Administration Guide | 5 | To Do | To Do | To Do | No Change | To Do | To Do
|  | OPT-PRM-029 - Annalise Enterprise Performance Guide | 4 | To Do | To Do | To Do | No Change | To Do | To Do
|  | OPT-PRM-103 Annalise Enterprise User Guide (US) | 2 | To Do | To Do | To Do | No Change | No Change | No Change
|  | OPT-PRM-104 - Annalise Enterprise Administration Guide (US) | 2 | To Do | To Do | To Do | No Change | No Change | No Change
|  | OPT-PRM-105 - Annalise Enterprise Performance Guide (US) | 2 | To Do | To Do | To Do | No Change | No Change | No Change
|  | OPT-PRM-057 Annalise Viewer Adapter for Sectra IDS7 Admin Guide | 0 | No Change | No Change | No Change | No Change | No Change | No Change
|  | OPT-PRM-007 - Third Party Software and Licences | 8 | To Do | To Do | To Do | No Change | To Do | To Do
|  | OPT-PRM-008 Privacy Policy | 5 | No Change | No Change | No Change | No Change | No Change | No Change |  | Being worked on at the moment, may tie into release timing.
Regulatory Compliance | Device Description | OPT-RA-005 - Device Description | 12 | No Change | To Do | To Do | No Change | To Do | No Change | Kiet
| Regulatory Output | REG-ANN-016 Market Access of Device Configuration Register | 12 | To Do | No Change | CO | No Change | CO | To Do | Kingston | Register to indicate TB is NOT available in regional configs. @rejo to confirm approach
| Regulatory Change Assessment | OPT-RA-044 - Regulatory Change Assessment for Annalise Enterprise 3.6 | 10 | To Do | To Do | To Do | No Change | No Change | To Do | Kingston | Will do standalone for TB and Reporting
| Technical File | TF-RA-001 Technical File: Annalise Enterprise | 3 | To Do | CO | CO | No Change | CO | To Do
| EU MDR Checklist | OPT-RA-018 EU MDR GSPR Checklist | 3 | To Do | CO | CO | No Change | CO | To Do
| EU MDD Checklist | OPT-RA-023 - Essential Requirements and Essential Principles Checklist | 3 | To Do | CO | CO | No Change | CO | To Do
| TGA Essential Principles | OPT-RA-023 - Essential Requirements and Essential Principles Checklist | 3 | To Do | CO | CO | No Change | CO | To Do
Post Market | Maintenance and Support plan | OPT-PRJ-001 - Design & Development Plan | 12 | To Do | To Do | To Do | No Change | To Do | To Do
| Post-Market Surveillance Plan | OPT-QA-002 - Post Market Surveillance Plan for Annalise Enterprise | 6 | No Change | No Change | No Change | No Change | No Change | No Change | Rohan | Check if TB needs to be added
| Post-Market Clinical Follow-up Plan | OPT-QA-003 - Post Market Clinical Follow-up Plan for Annalise Enterprise | 6 | No Change | No Change | No Change | No Change | No Change | No Change | Rohan
| Post Market Report | OPT-CLI-104- Post-Market Clinical Follow-Up Report for Annalise Enterprise | 1 |  | No Change | To Do | No Change | No Change
| Post Market Data Report | OPT-QA-00

## Runsheet
Phase | Phase Area | Document | Version | Status
1 | Planning | ANA-PRJ-001 Design and Development Plan | 3 | Published
1 | Planning | ANA-PRJ-003 XFT Definition | 3 | Published
2 | Design Input | ANA-PRM-001 Use Specification | 2 | Published
2 | Design Input | ANA-PRM-002 Input Requirements | 2 | Published
2 | Design Input | OPT-RA-007 Applicable Standards and Guidance Documents | 15 | Published
2 | Design Input | ANA-RA-003 Regulatory Strategy Plan for HAI-Radx Suite CT Chest | 1 | Published
2 | Design Input | ANA-RA-005 Regulatory Change Assessment for HAI-RadX Suite CT Chest Drop 2 | 1 | Published
2 | Design Input | ANA-SYS-008 Software requirements - CT Chest | 5 | Published
2 | Risk Management | ANA-SYS-002 Risk Management Plan | 0 | No Change
2 | Risk Management | ANA-SYS-003 Risk Analysis Report | 4 | Published
2 | Risk Management | ANA-SYS-004 Cybersecurity Risk Analysis | 4 | Published
3 | Design Outputs | ANA-SYS-001 CTC Findings Specification | 4 | Published
2 | Design Outputs | ANA-SYS-015 Design Review Minutes for CT Chest Drop 2 | 1 | Published
2 | Design Outputs | ANA-SW-003 Software Architecture and Design Description | 2 | Published
2 | Design Outputs | ANA-SW-013 Harrison Open Platform DICOM Conformance Statement | 1 | Published
2 | Design Outputs | ANA-SW-006 CTC Models Development plan | 1 | Published
2 | Design Outputs | ANA-SW-007 CTC Models Development record | 2 | Published
2 | Design Outputs | ANA-SW-005 OTS Software acceptance Report | 5 | Published
2 | Design Outputs | ANA-SW-010 Container Release candidate - CT Chest | 9 | Published
2 | Design Outputs | ANA-PRJ-004 Design Transfer Plan | 1 | Published
2 | Design Outputs | ANA-SW-011 Software Configuration Management Plan | 0 | No Change
2 | Design Outputs | ANA-SW-021 Interface Specification | 4 | Published
2 | Design Outputs | ANA-SW-012 Installation Requirements | 1 | No Change
2 | Design Outputs | ANA-SYS-011 Device Description | 2 | Published
2 | Design Outputs | ANA-DPL-001 Clinical AI Containers Deployment Runsheet - Cloud | 0 | No Change
2 | Design Outputs | ANA-DPL-007 Clinical AI Containers Deployment Record - CTC 2.0.2 APSE2 Staging | 1 | Published
3 | Verification and Validation | ANA-VNV-001 Verification Plan | 2 | Published
3 | Verification and Validation | ANA-VNV-002 Container Verification Protocol | 4 | Published
3 | Verification and Validation | ANA-VNV-003 Container Performance verification Protocol | 2 | Published
3 | Verification and Validation | ANA-VNV-007 Container Verification Report | 3 | Published
3 | Verification and Validation | ANA-VNV-008 Container Performance verification Report | 2 | Published
3 | Verification and Validation | ANA-AD-001 Accompanying document verification checklist | 4 | Published
3 | Verification and Validation | ANA-AD-002 Accompanying document verification checklist results | 2 | Published
3 | Verification and Validation | ANA-SW-017 CTC AI Module Evaluation Pipeline CSV Protocol | 2 | Published
3 | Verification and Validation | ANA-SW-018 CTC AI Module Evaluation Pipeline CSV Report | 2 | Published
3 | Verification and Validation | ANA-SW-019 Container Unit and IntegrationTest Framework CSV Protocol | 1 | Published
3 | Verification and Validation | ANA-SW-023 Container Unit and Integration Test Framework CSV Report | 1 | Published
3 | Verification and Validation | ANA-VNV-012 Validation Plan and Protocol | 2 | Published
3 | Verification and Validation | ANA-VNV-013 Validation Report | 2 | Published
3 | Verification and Validation | ANA-VNV-014 Verification and validation summary (trace matrix) | 2 | Published
3 | Verification and Validation | ANA-PRJ-005 Deferred Issues | 2 | Published
3 | Verification and Validation | ANA-SW-024 Regression Analysis | 9 | Published
3 | Clinical Research and Evaluation | OPT-CLI-055 CTC Multi-Reader Multi-Case Study Protocol | 3 | No Change
3 | Clinical Research and Evaluation | OPT-CLI-056 CTC MRMC Statistical Analysis Plan | 1 | Published
3 | Clinical Research and Evaluation | OPT-CLI-157 CTC Multi-Reader Multi-Case Study Report | 1 | Published
3 | Clinical Research and Evaluation | OPT-CLI-112 Literature Review Protocol for Annalise CTC Module | 2 | Published
3 | Clinical Research and Evaluation | OPT-CLI-113 Literature Review Report for Annalise CTC Module | 1 | Published
3 | Clinical Research and Evaluation | OPT-CLI-131 Literature Evaluation Matrix for Annalise CTC Module | 1 | Published
3 | Clinical Research and Evaluation | OPT-CLI-137 CTC Standalone and Module versus Reader Study Protocol | 1 | Published
3 | Clinical Research and Evaluation | OPT-CLI-139 CTC Ground Truth Labelling Schema | 1 | No Change
3 | Clinical Research and Evaluation | OPT-CLI-149 CTC Reader Labelling Schema | 0 | No Change
3 | Clinical Research and Evaluation | OPT-CLI-151 CTC MRMC Findings under Evaluation | 1 | Published
3 | Clinical Research and Evaluation | OPT-CLI-152 CTC MRMC Test Set Record | 0 | No Change
3 | Clinical Research and Evaluation | OPT-CLI-155 CTC Standalone and Module versus Reader Statistical Analysis Plan | 2 | Published
3 | Clinical Research and Evaluation | OPT-CLI-156 CTC Standalone and Module versus Reader Study Report | 2 | Published
3 | Clinical Research and Evaluation | Annex A to OPT-CLI-156 CTC Standalone and Module vs Reader Study (DOC-5899) | 0 | No Change
3 | Clinical Research and Evaluation | OPT-CLI-158 CTC Performance Evaluation Summary | 3 | Published
3 | Clinical Research and Evaluation | OPT-CLI-161 CTC MRMC Data Monitoring Report | 1 | Published
3 | Clinical Research and Evaluation | OPT-CLI-163 CTC Data Cleaning & Handling Report | 3 | Published
3 | Clinical Research and Evaluation | OPT-CLI-169 CTC Standalone and Module versus Reader Findings and Attributes Under Evaluation | 4 | Published
3 | Clinical Research and Evaluation | OPT-CLI-170 CTC Medical Image Labelling Report | 1 | Published
3 | Clinical Research and Evaluation | OPT-CLI-171 CTC Training Dataset Description | 0 | No Change
3 | Clinical Research and Evaluation | ANA-CLI-012 HAI-RadX Suite Module Comparison Protocol | 1 | Published
3 | Clinical Research and Evaluation | ANA-CLI-013 HAI-RadX Suite Module Comparison Report | 1 | Published
3 | Clinical Research and Evaluation | ANA-CLI-010 Benefit-Risk Analysis | 1 | Published
3 | Clinical Research and Evaluation | OPT-CLI-042 Clinical Evaluation Plan | 9 | Published
3 | Clinical Research and Evaluation | OPT-CLI-044 Clinical Evaluation Report | 10 | Published
3 | Clinical Research and Evaluation | OPT-QA-003 Post Market Clinical Follow-up Plan | 12 | No Change
3 | Guides | ANA-PRM-020 HAI-RadX Suite CT Chest User Guide | 1 | Published
3 | Guides | ANA-PRM-020-A Annex A HAI-RadX Suite CT Chest Performance Guide | 1 | Published
3 | Guides | ANA-PRM-022 HAI-RadX Suite CT Chest Administration Guide | 1 | Published
4 | Design transfer and release | ANA-SW-032 HAI-RadX Suite CT Chest Release report | 1 | CO
4 | Design transfer and release | ANA-SW-031 HAI-RadX Suite CT Chest Software BOM | 1 | CO
4 | Design transfer and release | ANA-PRM-025 HAI-RadX Suite CT Chest 2.0 Release Notes | 0 | Published
4 | RAQA Compliance | REG-ANN-016 Market Access of Device Configuration Register | 54 | Market Release
4 | RAQA Compliance | TF-RA-004 Technical File HAI-RadX Suite | 6 | Market Release
4 | RAQA Compliance | MRA-RA-013 HAI-RadX Suite GSPR, EP, ER checklist | 1 | Market Release
4 | RAQA Compliance | MRA-RA-008 eIFU of MD Regulation (EU) 2021/2226 Compliance Assessment | 2 | No Change
4 | RAQA Compliance | OPT-QA-006 IEC 62304 Checklist | 1 | Published
4 | RAQA Compliance | ANA-QA-001 IEC 82304-1 Checklist | 1 | Published
5 | Post Market Suveillance | OPT-QA-002 Post Market Surveillance Plan | 10 | Published

## _56F9DC9755BA473782653E2940F9 (hidden)
5GiBSv6hlku-Gt1g1OeCa5Nese5sHtlKla7LDEj0-o5UMDE0VlZIT05OQVJKWlNGUlozM0E1UktTNCQlQCN0PWcu
Form1
{893f0bca-96db-4f93-ab69-207fba26f516}